## Tabelle1
Sprint Review Protocol
Sprint No: |  | 1
Date & Time |  | 2024-04-02
Group Number |  | 11
Participant 1 |  | Halwax Jan
Participant 2 |  | Leitgeb Raphael
Participant 3 |  | Armin Naseri
Participant 4 |  | Andy Mihalca
Participant 5 |  | Ibrahim Barakat
Mentor |  | Konrad Jürgen
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | landingpage | 1 | 1 | 0
2 | registerpage | 2 | 2 | 0
3 | loginpage | 2 | 2 | 0
4 | impressum | 1 | 1 | 0
5 | firebase projekt aufgesetzt | 3 | 5 | 2
6 |  |  |  | 0
7 |  |  |  | 0
… |  |  |  | 0
… |  |  |  | 0
n |  |  |  | 0
7 |  |  |  | 2 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol